## Production
Component	Qty	Points / Component	Total points
Resistors	7	2	14
Capacitor Disc	3	2	6
Capacitor Electorlytic	3	2	6
LED	2	2	4
Crystal	1	2	2
Diode	2	2	4
Regulator (7805)	1	3	3
Transistor	1	3	3
Relay	1	4	4
Fuse holder	1	2	2
Reset button	1	4	4
Screw Connector	3	2	6
Female Bug strip 6 pin	1	6	6
IC base	1	28	28
Jumper	3	2	6

		Total points	98
Time Per point	25	s
Total time per board	2450	s
	40.83	mins
Total boards	200
Total time	490000	s
	136.11	Hrs

Hours per day	5	Hrs
Time in days	27.222	days
Persons	2.5
Time in days	10.8888

## Programming & Testing
No of Borads	200			Testing
				Bluetooth App Setup time	300	s
				Bluetooth Unpair and repair	180	s
Boot Loader Lodaing
Setup time	1800	s		Tests
Load Time	30	s		On test	5
Total time	6000	s		Off	5
	100	mins		On 5 sec	10
No of sessions	4			Self Test	5
Session time	25	mins		Emergency Stop	5
Seesion break	5	mins
				Test Time / board	210	s
Total time	150	mins		Total time	42300	s
					11.75	Hrs
Code Loading
Setup time	5	mins		No of persons	1
Load Time	30	s		Hours / day	3
Total time	6000	s		No of days	3.9166666667	days
	100	mins
No of sessions	4
Session time	25	mins
Seesion break	5	mins
				Testing + Programming	5	days
Total time	120.08	mins

Time	1	day

## Plan
Task	Days	Comment
Production	14	4 persons
Programming & Testing	7	1 person

	21	days
Efficency	60	%
Total time	35	days

Start of work	27 Sep 2019
End of Work	1 Nov 2019